Buyer exit and transition guidance
RM6202
Tail Spend Solution

Last updated: 11 May 2026
# Purpose of this document
This document provides guidance to customers on implementing a successful exit strategy from RM6202 Tail Spend Solution and transitioning to RM6369 The Marketplace. The objective is to ensure a seamless handover of services and data back to the Buyer and/or the Awarded Supplier of RM6369 The Marketplace with minimal disruption.
The Marketplace Category Team is available to answer questions you may have after reading this document, questions and meeting requests can be sent via email to themarketplace@gca.gov.uk.
# Exit and transition guidance
This section covers actions that Buyers need to take and when to ensure a smooth transition from RM6202 to RM6369. The suggested timeline is designed to ensure that you maintain service continuity while managing the commercial and technical complexities of moving from RM6202 to RM6369.

## Phase 1: Strategic assessment, 9-12 months before call-off contract expiry
The primary goal of this phase is to determine your transition window and initiate contact with the RM6369 Awarded Supplier.
Step	Instruction
	Review extension options / Check your existing RM6202 call-off contract to see if there are any remaining optional extension periods. Deciding early whether to trigger an extension can provide a critical "buffer" if the transition to RM6369 appears complex. / Please note that under RM6202 call-off contracts cannot exceed a maximum term of four years including any optional extension periods.
	Initial supplier engagement / Engage with the awarded RM6369 framework supplier to confirm their capability to meet your specific needs and to ascertain their standard implementation/onboarding lead times, you should provide them with a high-level overview of your current service requirements. Use data to accurately define your requirements, ensuring you clearly identify the value and categories of purchases.
	Establish internal governance / Appoint a Transition Manager and a cross-function team (Procurement, IT, Legal) to oversee the exit from RM6202 and the commencement of RM6369.
	TUPE review / Check with your current supplier if TUPE applies to your call-off contract and take action based on the response.

## Phase 2: Transition planning, 6-9 months before call-off contract expiry
This phase involves deep-diving into the technical requirements for moving your data and services.
Step	Instruction
	Finalise exit plan / Formalise the exit process with your current supplier.
	Map requirements / Compare your existing service levels under RM6202 against the offerings in RM6369. Identify any gaps or new requirements that need to be captured in the new call-off contract.
	Asset and data audit / Conduct a full audit of all customer-owned assets and data hosted by the current supplier. Ensure you have a clear understanding of data formats to prevent "vendor lock-in" during the migration.

## Phase 3: Detailed execution, 3-6 months before expiry
At this stage, you should be finalising the new call-off contract.
Step	Instruction
	Finalise RM6369 call-off contract / Complete the call-off contract for the RM6369 supplier. Ensure that the commencement date of the new contract aligns with (or slightly overlaps) the expiry of the RM6202 contract to avoid service gaps. A copy of the signed call-off contract should be shared with GCA by emailing a copy to themarketplace@gca.gov.uk.
	Knowledge transfer / Ensure that the new supplier is aware of system requirements such as approvals and ERP integrations.

## Phase 4: Migration and cutover, 0-3 months before expiry
The focus shifts to the physical migration of services and data.
Step	Instruction
	Finalise implementation plan / Work with the awarded supplier to finalise your implementation plan ensuring that all requirements are captured, including set up requirements.
	Pilot/trial migration / Conduct a trial data export and import between your current supplier and new supplier. Validate data integrity and system performance in the RM6369 platform.
	Parallel running / If possible, arrange for a short period of parallel running where both the RM6202 and RM6369 services are active, allowing for real-time validation before the RM6202 contract officially expires.

## Phase 5: Post-expiry, 0-3 months post-expiry

This is the final stage focused on formally closing the RM6202 contract and ensuring secure data handling with the outgoing supplier.

Step	Instruction
	Data deletion / Ensure the outgoing RM6202 supplier has deleted (required) data and that you and the new supplier have received applicable data.
	Final financial reconciliation / Review and settle all final invoices, service credits, or outstanding charges with the RM6202 supplier to formally close the contract. GCA to be made aware of when the last invoice has been settled to ensure that all management information has been reported by the supplier to GCA. GCA can be contacted at themarketplace@gca.gov.uk.