Buyer guide to mobilisation
RM6232
Facilities Management and Workplace Services
## Mobilising a contract
CCS Procurement Essentials

Once you’ve awarded a supplier for your requirement, it’s time to think about effective contract management. This starts with mobilisation, and this guide will help by pointing out some key areas for consideration.

### Mobilisation
Mobilisation happens after you’ve awarded your supplier, but before the contract goes live. You should set aside appropriate time to gather together all the information you need to run the contract and make sure that the right plans are in place.

For those colleagues in buyer’s organisations who shall have responsibilities for managing the mobilisation period, you should be engaged throughout the procurement process (from developing the requirements through to award of the contract). This will enable you to become familiar with all contractual requirements relating to mobilisation obligations and processes prior to award which will support and efficient transition of services during the mobilisation period.

Mobilisation of a contract can vary depending on the contract value, length and complexity of the requirement. This should be considered to ensure that mobilisation is proportionate to the contract requirement to allow sufficient time. Mobilising a contract too quickly can create problems once the contract is in service.

A mobilisation plan is an essential tool at this stage, particularly for high-value or more complex procurements, and should contain:

- a summary of expectations
- details of all tasks to be completed and timescales, also known as milestones
- roles and responsibilities of both parties
- arrangements for any contractual “due diligence”, including monitoring performance and any ongoing assurance of supplier capability, such as their financial standing

The following guidance highlights the key schedules in the Public Sector Contract which will enable and support the mobilisation of your contract.

### Key schedules in the Public Sector Contract to support mobilisation
It is particularly important that you have read and are familiar with the following schedules as they contain key mobilisation requirements that the supplier should provide you with during the mobilisation period.

#### Call off schedule 13 (mobilisation plan and testing)
This outlines key mobilisation obligations, including the supplier providing you with a mobilisation plan, any mobilisation milestones you have set out and dealing with security requirements during mobilisation.

#### Call off schedule 5 (pricing details)
This outlines the requirement for the supplier to complete a data validation and asset verification audit in order to ensure accuracy of the due diligence information.
#### Call off schedule 8 (business continuity and disaster recovery)

This outlines the requirement for the supplier to provide you with a business continuity and disaster recovery plan.
#### Call off schedule 28 (TUPE surcharge)

Where the award of your contract involves TUPE (Transfer of Undertakings (Protection of Employment) Regulations), this outlines the process for agreeing any associated TUPE risk premium, depending on the option you have selected.

#### Call off schedule 5 (key performance indicators)
This schedule outlines what will happen if the supplier fails to meet the key performance indicators and also includes the key performance indicators specific to your contract.

### Mobilisation checklist
Have you read and reviewed the terms and conditions, in particular:
call off schedule 13 (mobilisation plan and testing)

call off schedule 5 (pricing details)

call off schedule 8 (business continuity and disaster recovery)

call off schedule 28 (TUPE surcharge)

call off schedule 5 (key performance indicators)

have you read and understood the suppliers tender (including any supporting documents such as mobilisation plans, risk registers, communications plans)

are key stakeholders available for early engagement and have these sessions been scheduled?

have you considered TUPE implications?

have you received all the information as per the table within annex A (below) - contractual requirements?

### Market insight and best practice
Mobilising any contract can bring about a number of challenges however the following hints and tips below should help to prevent / mitigate against these.

#### Ensure you have a good understanding of what you have procured
It is vital that you understand all parts of the supplier’s tender, including:

your contract, including the specification, order form, core terms, call off and joint schedules (or appropriate industry term contract data)

the performance measures that you have included, for example any mobilisation milestones and key performance indicators

the suppliers ‘bid’. This will include the supplier’s commitments and obligations; these will be both contractual and made as part of the bid. The bid will often include themes and key activities within their quality responses which need to be enacted during the mobilisation period

Where a mobilisation plan and supporting information has been provided as part of the tender response it is key to understand this to ensure that it fits with your own mobilisation plans and any issues can be resolved prior to the contract start date

early collaboration is key and will help to build an effective working relationship moving forward

#### Consider stakeholder availability and engage early
Each mobilisation is a time-consuming operation and should not be supplier led. It is vital that key stakeholders from your organisation are available to be part of mobilisation and work stream calls, workshops and engagement sessions.

Where possible, early engagement through kick off sessions, work stream deep dives and stakeholder engagement should start as soon as possible. There can often be a significant pause post contract signature, prior to mobilisation and this delay can cause the loss of momentum.

In addition to mobilisation, there will be the transition phase before a move to business as usual. It’s important to bear in mind that this transition phase is just as important as mobilisation and requires clear objectives and timelines with the right stakeholders available to support.

#### Allow sufficient time for the supplier to mobilise and complete the asset verification audit during this period

It is important that the supplier is allowed enough time to complete all the activities associated with mobilisation and set up the contract effectively.

There will be a significant period of data verification by the new supplier to identify any data provided during the tender that is missing, inaccurate or wrong. This data will be from all service lines, employee details and includes asset data, hours worked, salary, payment, pensions and can have a big impact on the final price of the services.

It is critical that the supplier is allowed enough time to complete this activity and the asset verification audit within the mobilisation period. Allowing this activity to extend into the service delivery period could cause significant issues later on.

#### Ensure effective risk management

Risk registers are normally submitted as part of the tender, therefore these should be reviewed formally at the earliest opportunity in a risk session including both buyer and supplier. Mitigating risks is in both parties’ interest and if there is a significant risk that has been missed within the tender process then this will need working through collaboratively.

#### Carefully consider any staff transfer

Staff transfer is worrying, especially for long-serving colleagues and so communications around this is crucial. Communications plans are often submitted as part of the bid and you must review these thoroughly to ensure that they are fit for purpose and fully developed.

There may be friction between the new and old supplier so you need to be prepared to support both through any issues to ensure a smooth transition.

There will also be key staff that are critical for success, this needs to be considered and managed to retain expertise and knowledge.

There are clear timelines for TUPE transfers and engagement to occur, scheduling these in with other stakeholders such as human resources, union representatives and in a timeframe that doesn’t impact service delivery can be a challenge.

#### Think carefully about the logistics

The logistical details (including deliveries depending what services are in scope) will often cause frustrations/delays and these need thinking through carefully. Key issues often arise around access to sites for new supplier teams for staff engagement, deliveries of goods, asset data verification and systems so it’s important that you consider these early on to mitigate any issues where you can.

### Be aware:
any significant timeline changes to the tender and mobilisation can have a big impact on the mobilisation plan. At its simplest, it could just require an update of all the milestone dates; but at the most complex it could cause the compression of timelines and significant changes to work stream plans

for most suppliers, a sales/commercial team will hand over the tender responses to a mobilisation/operations team to deliver. Many will include the mobilisation team in the tender response planning but this isn’t always the case

there is a chance that a supplier can prepare and submit a low scoring/poor mobilisation technical response/plan and still be awarded the contract due to strong answers in other areas. If this is the case, it is important that you engage to ensure that the mobilisation does not fail

costs can dramatically increase as a result of the asset verification audit as a result of incomplete/inaccurate information such as asset data and staffing hours

## Annex A - Contractual requirements

What is required	By who	When	Schedule
Draft transparency report	Supplier	Within 3 months of the start date	RM6232 Call off schedule 1 transparency reports v1.0
Continuous improvement plan	Supplier	Start of each contract year	RM6232 Call off schedule 3 continuous improvement v1.0
Data validation and asset verification audit	Supplier	During the mobilisation period	RM6232-Call-Off-Schedule-5-Pricing-Details-v2.0
Business continuity and disaster recovery plans	Supplier	At least ninety (90) working days prior to the start date	RM6232 Call off schedule 8 business continuity and disaster recovery v1.0
Short and Long form / Security management plan	Supplier	Within twenty (20) working days after the start date	RM6232 Call off schedule 9 security v1.0
Long form only / Information security management plan	Supplier	Within twenty (20) working days after the start date	RM6232 Call off schedule 9 security v1.0
Copy of its depreciation policy to be used for the purposes of calculating net book value	Supplier	Within thirty (30) days from the start date	RM6232 Call off schedule 10 exit management v1.0
Exit plan	Supplier	Within three (3) months after the start date	RM6232 Call off schedule 10 exit management v1.0
Appoint exit manager	Buyer/Supplier	Within three (3) months of the start date	RM6232 Call off schedule 10 exit management v1.0
Draft mobilisation plan	Supplier	Within the timescales set by the buyer within call off schedule 12	RM6232 Call off schedule 13 mobilisation plan and testing v.1.0
TUPE surcharge options 1 (direct award) and 2 (further competition TUPE risk premium) only / Provide notice that no adjustment is required and the further competition TUPE risk premium submitted at call-off tender will be used. / or / The updated calculation of the further competition TUPE risk premium together with a breakdown and supporting evidence	Supplier	No later than twenty (20) working days after the relevant transfer date	RM6232 Call off schedule 28 TUPE surcharge v1.0
Evidence, in a form satisfactory to the relevant authority, that the Insurances are in force and effect and meet in full the requirements of the schedule.	Supplier	Upon the start date and within fifteen (15) working days after the renewal of each of the insurances	RM6232 Joint schedule 3 insurance requirements v.1.0