## 2026
January 2026 Competition (05/12/2025 - 02/02/2026)
Action	Completion Date	Action Owner		Key
Customer to submit site addition template and pre-populated call-off to CCS	05/12/2025	Customer		Commercial Agreement Manager (CAM)
Aggregate customer site lists into master document (per lot)	08/12/2025 - 10/12/2025	CAM		Procurement Operations (PO)
Prepare Inviatation to Tender bid packs	08/12/2025 - 27/12/2025	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	02/01/2026	PO
Respond to supplier clarifications (Subject to change)	15/01/2026	CAM/ PO
Invitation to Tender Closes (Subject to change)	16/01/2026	PO
Evaluation of responses (Subject to change)	19/01/2026 - 20/01/2026	CAM/ PO
Issue award notification to suppliers	21/01/2026	PO
Create customer award templates (add price to customer site lists)	20/01/2026 - 23/01/2026	CAM
Issue award notification to customers	26/01/2026 - 31/01/2026	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	02/02/2026 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	02/02/2026 + 90 working days	Supplier
Contract Commences	02/02/2026 + 90 working days	Customer
	02/02/2026 + 90 working days
April 2026 Competition (07/03/2026 - 01/05/2026)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	06/03/2026	Customer
Aggregate customer site lists into master document (per lot)	09/03/2026 - 11/03/2026	CAM
Prepare Inviatation to Tender bid packs	09/03/2026 - 27/03/2026	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	01/04/2026	PO
Respond to supplier clarifications (Subject to change)	10/04/2026	CAM/ PO
Invitation to Tender Closes (Subject to change)	15/04/2026	PO
Evaluation of responses (Subject to change)	17/04/2026 - 20/04/2026	CAM/ PO
Issue award notification to suppliers	21/04/2026	PO
Create customer award templates (add price to customer site lists)	17/04/2026 - 24/04/2026	CAM
Issue award notification to customers	24/04/2026 - 29/04/2026	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/05/2026 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/05/2026 + 90 working days	Supplier
Contract Commences	01/05/2026 + 90 working days	Customer

July 2026 Competition (06/06/2026 - 01/08/2026)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	05/06/2026	Customer
Aggregate customer site lists into master document (per lot)	08/06/2026 - 10/06/2026	CAM
Prepare Inviatation to Tender bid packs	08/06/2026 - 26/06/2026	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	01/07/2026	PO
Respond to supplier clarifications (Subject to change)	10/07/2026	CAM/ PO
Invitation to Tender Closes (Subject to change)	15/07/2026	PO
Evaluation of responses (Subject to change)	17/07/2026 - 20/07/2026	CAM/ PO
Issue award notification to suppliers	21/07/2026	PO
Create customer award templates (add price to customer site lists)	17/07/2026 - 24/07/2026	CAM
Issue award notification to customers	24/07/2026 - 31/07/2026	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/08/2026 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/08/2026 + 90 working days	Supplier
Contract Commences	01/08/2026 + 90 working days	Customer

October 2026 Competition (05/09/2026 - 01/11/2026)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	04/09/2026	Customer
Aggregate customer site lists into master document (per lot)	07/09/2026 - 09/09/2026	CAM
Prepare Inviatation to Tender bid packs	07/09/2026 - 25/09/2026	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	01/10/2026	PO
Respond to supplier clarifications (Subject to change)	13/10/2026	CAM/ PO
Invitation to Tender Closes (Subject to change)	15/10/2026	PO
Evaluation of responses (Subject to change)	16/10/2026 - 20/10/2026	CAM/ PO
Issue award notification to suppliers	22/10/2026	PO
Create customer award templates (add price to customer site lists)	16/10/2026 - 23/10/2026	CAM
Issue award notification to customers	23/10/2026 - 30/10/2026	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/11/2026 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/11/2026 + 90 working days	Supplier
Contract Commences	01/11/2026 + 90 working days	Customer

## 2027
January 2027 Competition (05/12/2026 - 01/02/2027)
Action	Completion Date	Action Owner		Key
Customer to submit site addition template and pre-populated call-off to CCS	04/12/2026	Customer		Commercial Agreement Manager (CAM)
Aggregate customer site lists into master document (per lot)	07/12/2026 - 9/12/2026	CAM		Procurement Operations (PO)
Prepare Inviatation to Tender bid packs	07/12/2026 - 27/12/2026	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	05/01/2027	PO
Respond to supplier clarifications (Subject to change)	14/01/2027	CAM/ PO
Invitation to Tender Closes (Subject to change)	15/01/2027	PO
Evaluation of responses (Subject to change)	18/01/2027 - 19/01/2027	CAM/ PO
Issue award notification to suppliers	20/01/2027	PO
Create customer award templates (add price to customer site lists)	19/01/2027 - 22/01/2027	CAM
Issue award notification to customers	25/01/2027 - 30/01/2027	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/02/2027 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/02/2027 + 90 working days	Supplier
Contract Commences	01/02/2027 + 90 working days	Customer
	01/02/2027 + 90 working days
April 2027 Competition (06/03/2027 - 30/04/2027)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	05/03/2027	Customer
Aggregate customer site lists into master document (per lot)	08/03/2027 - 10/03/2027	CAM
Prepare Inviatation to Tender bid packs	08/03/2027 - 25/03/2027	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	31/03/2027	PO
Respond to supplier clarifications (Subject to change)	09/04/2027	CAM/ PO
Invitation to Tender Closes (Subject to change)	14/04/2027	PO
Evaluation of responses (Subject to change)	16/04/2027 - 19/04/2027	CAM/ PO
Issue award notification to suppliers	20/04/2027	PO
Create customer award templates (add price to customer site lists)	16/04/2027 - 23/04/2027	CAM
Issue award notification to customers	23/04/2027 - 28/04/2027	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	30/04/2027 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	30/04/2027 + 90 working days	Supplier
Contract Commences	30/04/2027 + 90 working days	Customer

July 2027 Competition (05/06/2027 - 31/07/2027)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	04/06/2027	Customer
Aggregate customer site lists into master document (per lot)	07/06/2027 - 09/06/2027	CAM
Prepare Inviatation to Tender bid packs	07/06/2027 - 25/06/2027	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	30/06/2027	PO
Respond to supplier clarifications (Subject to change)	09/07/2027	CAM/ PO
Invitation to Tender Closes (Subject to change)	14/07/2027	PO
Evaluation of responses (Subject to change)	16/07/2027 - 19/07/2027	CAM/ PO
Issue award notification to suppliers	20/07/2027	PO
Create customer award templates (add price to customer site lists)	16/07/2027 - 23/07/2027	CAM
Issue award notification to customers	23/07/2027 - 30/07/2027	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	31/07/2027 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	31/07/2027 + 90 working days	Supplier
Contract Commences	31/07/2027 + 90 working days	Customer

October 2027 Competition (04/09/2027 - 01/11/2027)
Action	Completion Date	Action Owner
Customer to submit site addition template and pre-populated call-off to CCS	03/09/2027	Customer
Aggregate customer site lists into master document (per lot)	06/09/2027 - 08/09/2027	CAM
Prepare Inviatation to Tender bid packs	06/09/2027 - 24/09/2027	CAM/ PO
Publish Inviatation to Tender (1 per lot) (Subject to change)	30/09/2027	PO
Respond to supplier clarifications (Subject to change)	12/10/2027	CAM/ PO
Invitation to Tender Closes (Subject to change)	14/10/2027	PO
Evaluation of responses (Subject to change)	15/10/2027 - 19/10/2027	CAM/ PO
Issue award notification to suppliers	21/10/2027	PO
Create customer award templates (add price to customer site lists)	15/10/2027 - 22/10/2027	CAM
Issue award notification to customers	22/10/2027 - 29/10/2027	CAM
Customer to complete Framework Schedule 6 (contract) and send to Supplier	01/11/2027 + 90 working days	Customer
Supplier to countersign and return completed schedule 6 to Customer & CCS	01/11/2027 + 90 working days	Supplier
Contract Commences	01/11/2027 + 90 working days	Customer